TETSWORTH COMMUNITY-LED PLAN 2015-2025

John Gilbert

It is now a decade since Tetsworth launched its Community-Led Plan. Back in 2014, the project investigated all aspects of village life and documented actions that could make Tetsworth an even better place to live in within a 10 year timescale. No fewer than 46 ideas were identified. Each was fleshed out with details of how, when and by whom they might be implemented.

So, we are now 10 years on and it is time to report what happened to the 46 ideas. Using traffic light colour coding, 25 achieved green status and another 13 are graded amber. 8 came to a red light full stop either because they were impractical or failed to attract volunteers to take them forward.

Successes included the refurbishment of the heating and kitchen in the Memorial Hall and the mass planting of daffodils along our roadside verges. A couple of the non-starters were bringing natural gas to village households and something as simple as preparing an information pack for new village residents and visitors.

Hard copies of the CLP document were distributed to all Tetsworth households at the start of 2015 and a digital copy and the final version of the Action Chart documenting the outcome of all 46 ideas has been posted on the Parish Council website.