## Clerk List
TPC CLERK'S REPORT APRIL 2026
ACTION | MINUTE REF | RESPONSIBILITY | STATUS
Councillor actions
Clerk Ongoing Items
Monitor OCC investigation of school extension project progress. OCC met developer in Dec 23 to discuss S278 and S106 agreements. Land transfer to OCC and S278 agreement awaiting its registration with Land Registry, now anticipated by 23 Oct 25. OCC will meet with school head and governors after land transfer to confirm future plans. Cllr Judith Edwards to investigate and chase for update. JG has sent email to FvM - Clerk chased 28/11 for response. Response received from FvM Jan26 - chasing internally and will provide update. | 355c/21 | (OCC):JE
Clerk High Priority Items
Harlesford Community benefit deed paperwork. Chase for sign off at October meeting. Chased 9/9. Chased 28/11. Clerk has contacted solicitor to check legality of proposal. Quote received from solicitor to oversee benefit deed. Contribution from Bev to be considered. Agreed 2/26 Meeting to proceed with Kidd Rapinet Solicitors. Ongoing | 117d/25 | Clerk
Awaiting updated quotation from Fearless Ramps. | 117g/25 | Clerk
Asset Valuation register - two quotations received - for consideration and approval May meeting
Guttering repairs for TSSC. 4 x companies contacted for quotations. Awaiting responses.
Expression of interest - Flood Grant. EoI submitted. 1 x quotation received for the intended works and awaiting responses from 2 further contractors.
Insurance review - Gallaghers - submit for approval at May meeting.
Email from MoP regarding memorial bench - to discuss at May meeting
To seek quotation from Creative Play. Quote received and to be discussed May meeting.
Tree Survey - awaiting quotations.
AGAR 2025/26 - Accounts prepared and ready for sign off at May meeting
Clerk Low Priority Items
Write to Thames Water, SODC Environmental Health and OCC Highways concerning village drainage and flooding issues. Chair has prepared letter yet to be sent as awaiting key contact details from parishioner. Clerk to follow up. ONGOING. | 275/24
Investigate means of deterring unauthorized vehicle access to Village Green. Variety of post and chain boundaries seen in neighbouring parishes. Need to be monitored for one year from June 2024. ONGOING | 174b/23
Canvass support for possible First Aid training. More than 12 residents registered interest. Possible course dates post April 2023 investigated. No local face to face training available. Re-visit when practicable. ON HOLD | 448b/21