## Clerk List
TPC CLERK'S REPORT MARCH 2026
ACTION | MINUTE REF | RESPONSIBILITY | STATUS
Councillor actions
Clerk Ongoing Items
Monitor OCC investigation of school extension project progress. OCC met developer in Dec 23 to discuss S278 and S106 agreements. Land transfer to OCC and S278 agreement awaiting its registration with Land Registry, now anticipated by 23 Oct 25. OCC will meet with school head and governors after land transfer to confirm future plans. Cllr Judith Edwards to investigate and chase for update. JG has sent email to FvM - Clerk chased 28/11 for response. Response received from FvM Jan26 - chasing internally and will provide update. | 355c/21 | (OCC):JE
Clerk High Priority Items
Harlesford Community benefit deed paperwork. Chase for sign off at October meeting. Chased 9/9. Chased 28/11. Clerk has contacted solicitor to check legality of proposal. Quote received from solicitor to oversee benefit deed. Contribution from Bev to be considered. Agreed 2/26 Meeting to proceed with Kidd Rapinet Solicitors. Ongoing | 117d/25 | Clerk
Investigate moving from manual monthly/annual accounting to digital portal. Clerk to investigate and discuss at 3/26 meeting. Meeting held with Scribe VN/SM. Decided not to proceed. Discuss 4/26 mtg
Internal Audit 25/26. Quote agreed 3/26 mtg.
Skate ramp repairs - clerk to investigate composite alternative in addition to wooden replacement quotation received from Fearless ramps. Contact skatelite and report back. Scott Campbell - Surface Matter and Rob Steele - Radi Ramps - need quotation but will charge for site visit ? Discuss with TPC 3/26 meeting. Mtg held with SM. Update 4/26 mtg. | 117g/25 | Clerk
Kissing gate - Oxfordshire Way - Stoke Talmage & Parkers Hill access points - clerk to chase Countryside Access Officer further to last mtg that took place in Dec 2024. Done 9/9. Response received 26/9. Chair to respond. Clerk chased 28/11. Awaiting response. | OF 09/25 | Clerk/SM
Asset Valuation register - request to get assets valued ie TSSC - last update 2017. Clerk contacted GH. GH has made contact with OCC. Response received 9/2/26 - Bruton Knowles. Teams call taaken place. Awaiting quote. Discuss 4/26 mtg
TSSC Lease renewal quotations. Two quotations received. To discuss and finalise 4/26 mtg.
AGAR 2025/26 - Offficial notification received. AGAR underway. EOY reconcilation, EOY Balances to be agreed at 4/26 mtg.
Community Benefit deed. Correspondence received from Kidd Rapinet Solicitors. Response required. Discuss 4/26 mtg.
Play equipment - query regarding roundabout. Response received.
Recently installed salt bin at Judds Lane - needs repositioning as encroaching on private property - clerk to contact council to organise. Clerk chased 27/11. Clerk chased 17/12, 8/1/26, 12/1/26, 13/1/26. Chased again 2/3/26. Response received and on list for action. |  | Clerk
Clerk Low Priority Items
Write to Thames Water, SODC Environmental Health and OCC Highways concerning village drainage and flooding issues. Chair has prepared letter yet to be sent as awaiting key contact details from parishioner. Clerk to follow up. ONGOING. | 275/24
Investigate means of deterring unauthorized vehicle access to Village Green. Variety of post and chain boundaries seen in neighbouring parishes. Need to be monitored for one year from June 2024. ONGOING | 174b/23
Canvass support for possible First Aid training. More than 12 residents registered interest. Possible course dates post April 2023 investigated. No local face to face training available. Re-visit when practicable. ON HOLD | 448b/21